ETL (local)
eCollision Oracle DB
AWS cloud hosting
Potential concerns:
1) Data latency -> minor as real-time is not necessary
2) (Relatively more) manual process and complexity in securing and transferring dump file (require ongoing monitoring and potential for human error) -> this can be replaced with automated processes
3) Local resources needed for ETL jobs run locally -> need a separate dedicated computer, and set contingency plans like laptop or cloud server failure, aka via backups
Potential alternatives:
* Integrate most of the steps into cloud services altogether (downfall: learning curve + costly)
* Streamline the ETL process with data pipeline tool: Apache Airflow, dbt, or AWS Step Functions (downfall: learning curve)
1) Identify/filter valid cases from Oracle table
1) AWS-RDS set up for managed PostgreSQL service
eCollision Fusion
 DB (PostgreSQL)
Staged PostgreSQL DB - pg_dump
2) Consolidating/merging Oracle and Analytics tables/columns into single tables/columns
2) Import data to RDS - pg_restore
eCollision Analytics DB
3) Finalization and validation
3) Set up security and access
4) Connect applications and users
5) Optional backup and monitoring
AWS cloud hosting
1) AWS-RDS set up for managed database hosting service
Potential concerns:
1) Costs
2) Additional learning curve in the earlier processes
eCollision Oracle DB
ETL (dbt)
2) Import data to RDS
1) Identify/filter valid cases from Oracle table
Overall approach – the most viable approach:
* Set up most ELT pipeline locally in a separate machine that have schedule run
* Connect to AWS-RDS for multiple users’ access
* Incrementally swap out local computer to cloud components on Snowflake/dbt/AWS
Snowflake/AWS Redshift data warehousing
Option #1: External cloud hosting
3) Set up security and access
2) Consolidating/merging Oracle and Analytics tables/columns into single tables/columns
4) Connect applications and users
eCollision Analytics DB
3) Finalization and validation
5) Optional backup and monitoring
Snowflake cloud hosting
Option #2: Direct hosting from Snowflake
Similar tasks as above
Periodic retrieval
1-time retrieval for 2015
and earlier data
Periodic retrieval
1-time retrieval for 2015
and earlier data